## Sheet1
PHASE: | PERSON RESPONSIBLE: | REQUIREMENT: | USER:
Interactive Development |  |  | CITY WORKERS
Build 1 - Development |  |  | CITY WORKERS
Development (Front/Back-End) |  |  | CITY WORKERS
| Mike | Graffiti Incident Documentation (Crew Info) | CITY WORKERS
| Jimmy | Graffiti Incident Documentation (Graffiti Info) | CITY WORKERS
| Jose | Graffiti Incident Documentation (Image Upload) | CITY WORKERS
| Julian | Graffiti Incident Documentation (Options) | CITY WORKERS
Unit Test |  |  | CITY WORKERS
Handover to Test |  |  | CITY WORKERS
Build 2 - Development |  |  | LAW ENFORCEMENT
Development (Front/Back-End) |  |  | LAW ENFORCEMENT
| Mike | Ability to view Incident Record Info & Crew Info | LAW ENFORCEMENT
| Jimmy | Ability to edit Graffiti Info | LAW ENFORCEMENT
| Jose | Ability to update Graffiti Info | LAW ENFORCEMENT
| Julian | Ability to update Suspect Info | LAW ENFORCEMENT
| Mike | Add label to image | LAW ENFORCEMENT
| Jimmy | Graffiti Incident Documentation (Options) | LAW ENFORCEMENT
| Jose | Image Upload | LAW ENFORCEMENT
| Julian | Graffiti Analysis (GA) Requirements (Frequency of Incidents) | LAW ENFORCEMENT
| Jimmy | Graffiti Analysis (GA) Requirements (Hot Spot: Calculation) | LAW ENFORCEMENT
| Mike | Graffiti Analysis (GA) Requirements (Hot Spot: Reporting) | LAW ENFORCEMENT
Unit Test |  |  | LAW ENFORCEMENT
Handover to Test |  |  | LAW ENFORCEMENT
Build 3 - Sync |  |  | BOTH
Sync Crew/Law Enforcement |  |  | BOTH
| Julian | System and Performance Requirements (UI Performance) | BOTH
| Julian | System and Performance Requirements (Operational Environment: Multiple Users) | BOTH
| Julian | System and Performance Requirements (Security Access) | BOTH
| Julian | System and Performance Requirements (Single Entry of Information) | BOTH
| Jose | System and Performance Requirements (Validation of Inputs) | BOTH
| Jose | System and Performance Requirements (Entry and Processing of Names) | BOTH
| Jose | System and Performance Requirements (Online Help) | BOTH
| Jose | System and Performance Requirements (Screens/UI) | BOTH
| Jimmy | System and Performance Requirements (Prototype Design/Process) | BOTH
| Jimmy | System and Performance Requirements (Error Message) | BOTH
| Jimmy | GITS Framework (Navigation Structure) | BOTH
| Jimmy | GITS Framework (User Login Management) | BOTH
| Mike | GITS Framework (Authorized Users: Information Entry/Maintnence) | BOTH
| Mike | GITS Framework (User Name) | BOTH
| Mike | GITS Framework (User Employee Number) | BOTH
| Mike | GITS Framework (User's Job Title) | BOTH
| Mike | GITS Framework (User Password) | BOTH
| Jimmy | GITS Framework (Allowable Access Areas: Subsystem) | BOTH
| Jose | GITS Framework (System Admin Menu) | BOTH
| Julian | GITS Framework (Print Authorized User Report: Whole System/Subsystem) | BOTH
| Jimmy | GITS Framework (System Level Authorized Users: Password Reset/Initialization) | BOTH
| Mike | Graffiti Reporting (GR) Requirements (Map of Incidents) | BOTH
| Julian | Graffiti Reporting (GR) Requirements (Sorted Record of Incidents) | BOTH
| Jose | Graffiti Reporting (GR) Requirements (Status Report) | BOTH
Interactive Test |  |  | CITY WORKERS
Build 1 - Test |  |  | CITY WORKERS
Test Planning |  |  | CITY WORKERS
Test Analysis and Design |  |  | CITY WORKERS
Test Execution and Recording |  |  | CITY WORKERS
Test Completion |  |  | CITY WORKERS
Build 2 - Test |  |  | LAW ENFORCEMENT
Test Planning |  |  | LAW ENFORCEMENT
Test Analysis and Design |  |  | LAW ENFORCEMENT
Test Execution and Recording |  |  | LAW ENFORCEMENT
Test Completion |  |  | LAW ENFORCEMENT